## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Late | Completed Date | Completed By | Description | Completed Checklist Items | Checklist Items | Labels
GNpQ71F-BEmCrUxFgqAuVGUAE64U | Create project plan | Project 3 | Completed | Important | Shannon Lindsay | Adele Vance | 2022-01-07 |  | 2022-01-02 | false | 2022-03-19 | Shannon Lindsay |  | 0/3 | Subtask 2;Subtask 1;Subtask 3
0P_I7fz9FEOk-dBMziZ_2GUAAAoQ | Task 1 | Project 3 | Completed | Low | Joni Sherman | Shannon Lindsay | 2022-01-01 |  | 2022-04-02 | false | 2022-02-17 | Shannon Lindsay |  | 0/2 | Subtask 2;Subtask 1
ClN545NeE0OottsZXGH6qWUAClJ8 | Task 2 | Project 1 | In progress | Urgent | Lee Gu | Shannon Lindsay | 2022-03-01 | 2022-03-01 | 2022-03-25 | false |  |  |  | 1/3 | Subtask 3;Subtask 2;Subtask 1
EnBRsPYTYUeL-1TFVdfmCGUAOgE- | Task 3 | Project 2 | Not started | Low | Joni Sherman and Diego Siciliani | Adele Vance | 2022-03-14 |  | 2022-03-26 | false |  |  |  | 1/3 | Subtask 3;Subtask 2;Subtask 1
e-AOJrIk90WIGQ1KnGAjs2UAHIx1 | Update documentation | Backlog | Not started | Medium | Shannon Lindsay | Shannon Lindsay | 2022-03-20 |  | 2022-04-15 | false
ljVI_v5b10mfFzF3RSVh8GUAFU-D | Task 4 | Project 1 | Not started | Medium | Lee Gu | Shannon Lindsay | 2022-03-20 |  | 2022-01-04 | false |  |  |  | 0/2 | Subtask 2;Subtask 1
hVuj4Isyi0eL_hitW6mSZ2UAPWmz | Task | Project 2 | Not started | Medium | Joni Sherman | Adele Vance | 2022-03-20 |  | 2022-11-04 | false
assidjJTCkyIfsWK4uh2_GUANyg8 | Task | Project 1 | Not started | Medium | Shannon Lindsay | Shannon Lindsay | 2022-03-02 |  | 2022-03-23 | false
Z2cdySLS30SrLfk8tQMikWUAAurZ | Task | Project 3 | Not started | Medium | Lee Gu | Shannon Lindsay | 2022-03-08 |  | 2022-03-25 | false
53OJhlVH1EO6oD0EwhIdFWUAArmW | Create outstanding videos | Backlog | Not started | Medium | Shannon Lindsay | Shannon Lindsay | 2022-03-20 |  | 2022-04-29 | false
DQlxxxRXDUuJX4W3NJM4ImUADyEI | Task | Project 3 | Not started | Medium | Joni Sherman | Adele Vance | 2022-03-20 |  | 2022-02-05 | false
s4PVKsrlCU6qF0zrzRyl-GUABoV6 | Task | Project 2 | Not started | Medium | Lee Gu | Shannon Lindsay | 2022-03-10 |  | 2022-03-14 | true
Q4wq8O7Lp0GykF2tuchJJGUAHwrF | Task | Project 3 | Not started | Medium | Joni Sherman | Shannon Lindsay | 2022-03-20 |  | 2022-01-04 | false
V51QdIjVQEugA4lZXdXGOGUAHfOb | Task | Project 2 | In progress | Important | Joni Sherman | Adele Vance | 2022-03-04 | 2022-07-03 | 2022-03-25 | false |  |  |  | 1/3 | Subtask 3;Subtask 1;Subtask 2
dXH6BvCTT0O9wcmnFi2RoWUALABq | Task | Project 1 | Completed | Important | Lee Gu | Shannon Lindsay | 2022-03-20 |  | 2022-03-25 | false | 2022-03-20 | Shannon Lindsay
urU7gy4WL02fGI45kE0UpWUAPIjN | Task | Project 2 | Not started | Low | Lee Gu | Shannon Lindsay | 2022-03-20 |  | 2022-04-29 | false
9z0-zxvFKEmll6_8znM3nWUABQE- | Task | Project 2 | Not started | Medium | Joni Sherman and Shannon Lindsay | Adele Vance | 2022-03-20 |  | 2022-04-15 | false
a8yaTkc5SU2sfsdaGp8YuWUAFXvE | Task | Project 3 | In progress | Important | Lee Gu | Shannon Lindsay | 2022-03-20 | 2022-07-03 | 2022-01-04 | false
TZ1_7_TClUOovyez5Kone2UAGwnr | Task | Project 1 | In progress | Low | Joni Sherman | Adele Vance | 2022-03-20 | 2022-07-03 | 2022-01-04 | false | [5 empty] | Purple
syIJ4eDGH0W6qYaxB6C5KWUAMgLu | Task | Project 1 | Completed | Urgent | Shannon Lindsay | Shannon Lindsay | 2022-03-20 |  | 2022-03-20 | false | 2022-03-20 | Shannon Lindsay
E3-vDpa570-XiPBIeGHLOWUAJyjJ | Task | Project 1 | In progress | Medium | Lee Gu | Shannon Lindsay | 2022-03-20 | 2021-03-14 | 2022-04-15 | false
CbBnd50F0kq2rDvdOMXIuWUANxg- | Task | Project 3 | In progress | Important | Joni Sherman | Adele Vance | 2022-03-10 | 2022-03-14 | 2022-03-25 | false |  |  |  | 0/3 | Subtask 1;Subtask 3;Subtask 2

## Plan name
Plan name | Project Plan
Plan ID | hdmie0o4ik2o71IQtS5Y8GUAGRrN
Date of export | 03/20/2022